## Project
DMAS - Meilensteine
Meilenstein | Datum | Aufwand [PT]
Daten in Snowflake geladen | erledigt
Daten in Pakete für Delta-Load aufgeteilt | 2025-01-13 | 0.5
Daten-Vorbereitung für KI-Anwendung erstellt | 2025-01-15 | 2
KI-Anwendung designt | 2025-01-21 | 3
KI-Anwendung implenemtiert | 2025-01-23 | 2
Ergebnis-Aufbereitung implementiert | 2025-01-27 | 1
Delta-Load implementiert | 2025-01-28 | 1
Test | 2025-01-29 | 1

## Budget
Budget
Account |  | Budget |  | Delta
Bezeichnung | CreaDt | Dt | [$] | [#d] | [$]
MBASUL200113
MBASUL200113 |  | 2025-01-27 18:18 | 366
MBASUL250121 | 2025-01-21 15:21 | 2025-01-21 15:21 | 400
MBASUL250121 |  | 2025-01-23 11:04 | 394 | 2 | -6 | -3
MBASUL250121 |  | 2025-01-27 18:19 | 382 | 4 | -12 | -3
MBASUL250121 |  | 2025-01-27 19:59 | 382 | 0 | 0
MBASUL250121 |  | 2025-01-28 09:17 | 376 | 1 | -6 | -6
MBASUL250121 |  | 2025-01-28 17:51 | 371 | 0 | -5
MBASUL250121 |  | 2025-01-28 19:40 | 362 | 0 | -9
MBASUL250121 |  | 2025-01-29 09:18 | 356 | 1 | -6 | -6
MBASUL250121 |  | 2025-01-29 11:04 | 356 | 0 | 0
MBASUL250121 |  | 2025-01-30 12:05 | 346 | 1 | -10 | -10
MBASUL250121 |  | 2025-02-05 14:38 | 345 | -25 | -1 | 0.04
MBASUL250121 |  | 2025-02-06 08:00 | 337 | 1 | -8 | -8
MBASUL250121 |  | 2025-02-06 17:19 | 329 | 0 | -8

## AoEC Files
Harvard Atlas of Economic Complexity
https://dataverse.harvard.edu/dataset.xhtml?persistentId=doi:10.7910/DVN/T4CHWJ
Dokument | Daten-Set | Size LP36131 | Download | Size SN Stage
|  | [MB] |  | [MB] | [Bytes] | Kompression
data_dictionary.pdf
hs92_country_country_product_year_1.dta |  | 189.0608 | 2025-01-21 11:01 | 53.2888 | 55877354 | 71.81%
hs92_country_country_product_year_1.csv |  | 321.1044 | 2025-01-21 11:01 | 64.6186 | 67757464 | 79.88%
2
3
4
5
6
7
8
9
hs92_country_country_product_year_6_1995_1999.dta |  |  | 2025-01-21 11:03 | 0
hs92_country_country_product_year_6_1995_1999.csv |  | 2479.0914 | 2025-01-21 11:03 | 401.8905 | 421412699 | 83.79%
location_country.csv | product_hs92 | 0.006 | 2025-01-21 11:07
location_group.csv | product_hs92 |  | 2025-01-21 11:07
location_group_member.csv | product_hs92 |  | 2025-01-21 11:07
product_hs12.csv | product_hs92 | 0.375 | 2025-01-21 11:07
product_hs92.csv | product_hs92 | 0.365 | 2025-01-21 11:07
product_services_unilateral.csv | product_hs92 |  | 2025-01-21 11:07
product_sitc.csv | product_hs92 |  | 2025-01-21 11:07

## HS92 Tab PRODUCT_COUNTRY_HS92
Tab PRODUCT_COUNTRY_COUNTRY_HS92
Field Name | Description | Data Typ | Notes
ID
country_id | United Nations Country M49 Codes | Integer | Can be joined with the location _country table within the classifications dataset for more detailed information | PARTNER_COUNTRY_ID integer,
partner_country_id | United Nations Country M49 Codes | Integer | Can be joined with the location _country table within the classifications dataset for more detailed information; Only applicable to country -partner-product-year tables | PRODUCT_ID integer,
product_id | Growth Lab assigned numerical product identifier | Integer | Can be joined with the product_hs92 table within the classifications dataset for more detailed information | YEAR integer,
year | Year of record | Integer | HS records start at 1995 | EXPORT_VALUE integer,
export_value | Current USD export value | Integer |  | IMPORT_VALUE integer,
import_value | Current USD import value | Integer |  | ECI float,
eci | Economic Complexity Index computed usings HS product data | Float | Variable applicable to the respective country-year, independent of individual product | COI float,
coi | Complexity Outlook Index computed using HS product data | Float | Variable applicable to the respective country-year, independent of individual product | PCI float,
pci | Product Complexity Index | Float

## Prod.vergleiche
Produktvergleiche
Eigenschaft |  |  | Snowflake | Databricks | Fabric | Datasphere
001 | Upload von Dateien
001.01 |  | Maximale Dateigröße |  |  |  | 200 MB
Note on I8: Balzer, Matthias: [Robert Dunst]

## Tab PRODUCTS
Tab PRODUCT
# Product_hs92 (2012)
Field Name | Description | Data Type | Notes | SQL
product_id | Growth Lab assigned numerical product identifier | Integer |  | product_id integer, | PRODUCT_ID integer, | StructField('product_id', IntegerType(), nullable=True),
code | code HS (1992) product | String |  | code string, | CODE string, | StructField('code', StringType(), nullable=True),
name_short_en | English short name of product | String | Growth Lab shortened version of official product name for display | name_short_en string, | NAME_SHORT_EN string, | StructField('name_short_en', StringType(), nullable=True),
product_level | Level of specificity of the code in hierarchy | Integer | One of [1, 2, 4, 6] | product_level integer, | PRODUCT_LEVEL integer, | StructField('product_level', IntegerType(), nullable=True),
top_parent_id | Product id of class containing code at the top of the hierarchy, or product level 1 | Integer |  | top_parent_id integer, | TOP_PARENT_ID integer, | StructField('top_parent_id', IntegerType(), nullable=True),
product_id_hierarchy | Chain of product ids showing product hierarchy | String |  | product_id_hierarchy string, | PRODUCT_ID_HIERARCHY string, | StructField('product_id_hierarchy', StringType(), nullable=True),
# Product_hs12 (2012)
product_id | Growth Lab assigned numerical product identifier | Integer |  | product_id integer, | PRODUCT_ID integer, | StructField('product_id', IntegerType(), nullable=True),
code | HS (2012) product code | String |  | code string, | CODE string, | StructField('code', StringType(), nullable=True),
name_short_en | English short name of product | String | Growth Lab shortened version of official product name for display | name_short_en string, | NAME_SHORT_EN string, | StructField('name_short_en', StringType(), nullable=True),
product_ level | Level of specificity of the code in hierarchy | Integer | One of [ 1, 2, 4, 6] | product_ level integer, | PRODUCT_ LEVEL integer, | StructField('product_ level', IntegerType(), nullable=True),
top_parent_id | Product id of class containing code at the top of the hierarchy, or product level 1 | Integer |  | top_parent_id integer, | TOP_PARENT_ID integer, | StructField('top_parent_id', IntegerType(), nullable=True),
product_id_hierarchy | Chain of product ids showing product hierarchy | String |  | product_id_hierarchy string, | PRODUCT_ID_HIERARCHY string, | StructField('product_id_hierarchy', StringType(), nullable=True),

## Tab LOCATIONS
Tab PRODUCT
# Product_hs92 (2012)
Field Name | Description | Data Type | Notes | SQL
product_id | Growth Lab assigned numerical product identifier | Integer |  | product_id integer, | PRODUCT_ID integer, | StructField('product_id', IntegerType(), nullable=True),
code | code HS (1992) product | String |  | code string, | CODE string, | StructField('code', StringType(), nullable=True),
name_short_en | English short name of product | String | Growth Lab shortened version of official product name for display | name_short_en string, | NAME_SHORT_EN string, | StructField('name_short_en', StringType(), nullable=True),
product_level | Level of specificity of the code in hierarchy | Integer | One of [1, 2, 4, 6] | product_level integer, | PRODUCT_LEVEL integer, | StructField('product_level', IntegerType(), nullable=True),
top_parent_id | Product id of class containing code at the top of the hierarchy, or product level 1 | Integer |  | top_parent_id integer, | TOP_PARENT_ID integer, | StructField('top_parent_id', IntegerType(), nullable=True),
product_id_hierarchy | Chain of product ids showing product hierarchy | String |  | product_id_hierarchy string, | PRODUCT_ID_HIERARCHY string, | StructField('product_id_hierarchy', StringType(), nullable=True),
# Product_hs12 (2012)
product_id | Growth Lab assigned numerical product identifier | Integer |  | product_id integer, | PRODUCT_ID integer, | StructField('product_id', IntegerType(), nullable=True),
code | HS (2012) product code | String |  | code string, | CODE string, | StructField('code', StringType(), nullable=True),
name_short_en | English short name of product | String | Growth Lab shortened version of official product name for display | name_short_en string, | NAME_SHORT_EN string, | StructField('name_short_en', StringType(), nullable=True),
product_ level | Level of specificity of the code in hierarchy | Integer | One of [ 1, 2, 4, 6] | product_ level integer, | PRODUCT_ LEVEL integer, | StructField('product_ level', IntegerType(), nullable=True),
top_parent_id | Product id of class containing code at the top of the hierarchy, or product level 1 | Integer |  | top_parent_id integer, | TOP_PARENT_ID integer, | StructField('top_parent_id', IntegerType(), nullable=True),
product_id_hierarchy | Chain of product ids showing product hierarchy | String |  | product_id_hierarchy string, | PRODUCT_ID_HIERARCHY string, | StructField('product_id_hierarchy', StringType(), nullable=True),